## Sheet1
Steps	Sub steps	Duration	Date
Website design	Agreeing requirements with the client	40hrs	04/05/18
	Consultations with design consultant and draft version using the Photoshop	80hrs	18/05/18
	Making changes and agreing final design	40hrs	25/05/18
Programming the website in HTML and CSS With Bootstrap from scratch without using any templates in order to meet better client’s requirements	Creating Bootstrap Navbar and Menu	8hrs	07/06/18
	Creating and styling landing section	4hrs
	Creating and styling “About” section	4hrs
	Creating links to local news websites and social media	4hrs
	Creating and stiling movie list using Bootstrap Carousel	16hrs
	Linking movies to IMDB website form more information	4hrs
	Creating and styling “News and information” section	4hrs
	Creating and styling “Pre-register” form using Bootstrap and CSS	8hrs
	Testing	20hrs	07/06/18
Presentation to the client and launching the website online		8hrs	08/06/18